## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | U-1 | As a user, I want to upload text datasets so that I can preprocess and clean them efficiently using parallel processing. | MUST HAVE | None | Harshini | 3- Completed
1 | 1 | U-1 | As a user, I want the system to remove noise (stopwords, symbols, etc.) and lemmatize words for clean text representation. | MUST HAVE | U-1 | Harshini | 3- Completed
2 | 2 | U-2 | As a user, I want to extract key features from text using TF-IDF and CountVectorizer so that topics can be analyzed. | MUST HAVE | U-1 | Harshini | 3- Completed
2 | 2 | U-2 | As a user, I want to perform topic modeling using LDA to understand major discussion themes. | MUST HAVE | U-1 | Harshini | 3- Completed
3 | 3 | U-3 | As a user, I want to apply semantic clustering using K-Means and embeddings to find meaning-based topic groups. | SHOULD HAVE | U-2 | Harshini | 3- Completed
3 | 3 | U-3 | As a user, I want to compare K-Means and LDA results to see which method performs better on my dataset. | SHOULD HAVE | U-2 | Harshini | 3- Completed
4 | 4 | U-4 | As a user, I want an interactive dashboard (Streamlit) to visualize clusters, topics, and execution time. | MUST HAVE | U-2,3 | Harshini | 3- Completed
4 | 4 | U-4 | As a user, I want to view silhouette scores and topic flow to evaluate clustering quality visually. | SHOULD HAVE | U-3 | Harshini | 3- Completed
4 | 4 | U-4 | As a user, I want to measure and compare execution times to understand performance improvements with parallelism. | COULD HAVE | U-3 | Harshini | 3- Completed
5 | 5 | U-4 | As a developer, I want to test, debug, and optimize the final dashboard for deployment. | MUST HAVE | U-2,3 | Harshini | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 58 | 18 | 22 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
U-1 | M-1 | Choose the data (refer to Day 3 PPT) — select either small, medium, or large text dataset. Read the data file — either by web scraping or importing as CSV/TXT files. Store the data in the database and fetch the data for processing. Do text cleaning: Remove unnecessary characters (e.g., emojis, special characters) Normalize the text: lowercasing, tokenizing, lemmatizing, POS tagging Use multiprocessing techniques to efficiently find word frequencies and their counts. | 2025-09-08 | 2025-09-12 | Harshini | Coding | 3- Completed | 5 | Day 1: 1; Day 2: 2; Day 3: 1; Day 4: 1
U-1 | M-2 | Validate tokenization and lemmatization using SpaCy | 2025-09-13 | 2025-08-17 | Harshini | System Test | 3- Completed | 4 | bar: Day 1 to Day 4
U-1 | M-3 | Store processed data into database for reuse | 2025-09-18 | 2025-09-20 | Harshini | Build | 3- Completed | 2 | bar: Day 1 to Day 2
SPRINT 2 BACKLOG
U-2 | M-1 | Apply TF-IDF vectorization to represent documents numerically | 2025-09-23 | 2025-09-25 | Harshini | Coding | 3- Completed | 4 | Day 1: 2; Day 2: 2
U-2 | M-2 | Train LDA model with multiple cores (parallelized) | 2025-09-26 | 2025-09-28 | Harshini | Coding | 3- Completed | 6 | Day 1: 3; Day 2: 2; Day 3: 1
U-2 | M-3 | Extract top keywords per topic and visualize with matplotlib | 2025-09-29 | 2025-10-03 | Harshini | Design | 3- Completed | 2 | bar: Day 1 to Day 2
SPRINT 3 BACKLOG
U-3 | M-1 | Generate sentence embeddings using SentenceTransformer | 2025-10-06 | 2025-09-10 | Harshini | Coding | 3- Completed | 5 | Day 1: 1; Day 2: 2; Day 3: 1; Day 4: 1
U-3 | M-2 | Apply UMAP for dimensionality reduction | 2025-09-11 | 2025-09-14 | Harshini | Regression Test | 3- Completed | 5 | Day 1: 1; Day 2: 2; Day 3: 2
U-3 | M-3 | Perform K-Means clustering and evaluate Silhouette Score | 2025-09-15 | 2025-10-18 | Harshini | Coding | 3- Completed | 5 | Day 1: 1; Day 2: 2; Day 3: 2
SPRINT 4 BACKLOG
U-4 | M-1 | Integrate K-Means and LDA outputs into Streamlit dashboard | 2025-10-20 | 2025-10-24 | Harshini | Coding | 3- Completed | 8 | Day 1: 2; Day 2: 3; Day 3: 2; Day 4: 1
U-4 | M-2 | Add Silhouette Score, Topic Flow, and Time Comparison visuals | 2025-10-27 | 2025-10-28 | Harshini | Design | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2
U-4 | M-3 | Final testing, optimization, and presentation prep | 2025-10-29 | 2025-10-31 | Harshini | System Test | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | Dataset not stored in database | Fixed DB issue & stored dataset
1 | 2 | Errors during preprocessing | Corrected script & preprocessed
1 | 3 | Multiprocessing function causing memory overflow | Optimized process pool and reduced chunk size
1 | 4 | Lemmatization skipping some tokens | Adjusted SpaCy pipeline and verified token counts
1 | 5 | Processed files not saving in correct format | Fixed file handling path and re-ran preprocessing
2 | 1 | TF-IDF vectorizer producing sparse matrix errors | Limited max features and fixed token pattern
2 | 2 | LDA model taking too long to converge | Enabled parallel jobs (n_jobs = cpu_count)
2 | 3 | Repeated stopwords in top keywords | Extended custom stopword list and retrained model
3 | 1 | UMAP dimension reduction failed | Adjusted parameters (n_neighbors, n_components)
3 | 2 | K-Means producing uneven clusters | Normalized embeddings before clustering
3 | 3 | Keywords not matching topic labels | Used cosine similarity with candidate labels
4 | 1 | Streamlit not displaying plots properly | Adjusted figure rendering with st.pyplot() and Plotly
4 | 2 | Caching causing stale results | Cleared Streamlit cache and updated function decorators
4 | 3 | Slow response during topic comparison | Optimized caching and parallelized K-Means/LDA calls

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-08-09 | 13/09/2025 | Harshini | Create a test case for DB storage | Skipping DB storage step | Choosing dataset correctly | Dataset stored successfully
2 | 1 | 15/09/2025 | 19/09/2025 | Harshini | Preprocess the dataset |  | Preprocessing as planned | Preprocessed data generated
3 | 1 | 15/09/2026 | 19/09/2026 | Harshini | Implement multiprocessing for faster text preprocessing | Manual sequential text cleaning | Using SpaCy for lemmatization and stopword removal | Parallel text processor implemented and validated for speed improvement
4 | 2 | 29/09/2025 | 2025-04-10 | Harshini | Apply TF-IDF and CountVectorizer for text feature extraction | Using raw text for topic modeling | Checking model outputs for topic relevance | Text converted to numerical features using TF-IDF successfully
5 | 2 | 2025-06-10 | 2025-10-10 | Harshini | Train LDA model for topic extraction |  | Visualizing top words per topic | LDA executed using multi-core processing and generated topic keywords
6 | 3 | 13/10/2025 | 17/10/2025 | Harshini | Generate sentence embeddings and apply K-Means clustering |  | Comparing topic patterns across models | K-Means clusters formed and analyzed using embedding similarity
7 | 4 | 20/10/2025 | 25/10/2025 | Harshini | Integrate K-Means and LDA outputs into Streamlit dashboard | Testing models separately | Monitoring output quality and visualization accuracy | Streamlit dashboard built with topic comparison and timing visualizations