## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Harshini | 2025-09-12 | Dataset not saving in database | Sprint 1 | Harshini | Logical | Fixed DB connection and verified data write | 2025-09-13 | Closed | Working as expected
2 | Harshini | 2025-09-16 | Errors during multiprocessing step | Sprint 1 | Harshini | Logical | Adjusted process pool size and memory allocation | 2025-09-17 | Closed | Execution stable
3 | Harshini | 2025-09-20 | TF-IDF output matrix too large | Sprint 2 | Harshini | Maintainability | Reduced max features and limited vocabulary | 2025-09-21 | Closed | Optimized successfully
4 | Harshini | 2025-09-24 | Stopwords still visible in LDA topics | Sprint 2 | Harshini | Standards | Added extended stopword list and retrained model | 2025-09-25 | Closed | Topics improved
5 | Harshini | 2025-09-28 | Uneven cluster distribution in K-Means | Sprint 3 | Harshini | Logical | Normalized embeddings and re-ran clustering | 2025-09-29 | Closed | Clusters balanced
6 | Harshini | 2025-10-04 | Sankey diagram links not displaying properly | Sprint 4 | Harshini | User Interface | Fixed index mismatch in node mapping | 2025-10-05 | Closed | Diagram functional
7 | Harshini | 2025-10-07 | Streamlit cache not updating new data | Sprint 4 | Harshini | Maintainability | Cleared cache and updated decorators | 2025-10-08 | Closed | Dashboard responsive
8 | Harshini | 2025-10-10 | Visual overlap in time comparison chart | Sprint 4 | Harshini | User Interface | Adjusted plot layout and axis spacing | 2025-10-11 | Closed | Display corrected
9 | Harshini | 2025-10-13 | Slow dashboard load time | Sprint 4 | Harshini | Standards | Optimized resource loading and caching | 2025-10-14 | Closed | Performance improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others